## RSP Dates
Instrument ID | Instrument Short Name | RDC Implementation Need | Program Scope | Fiscal Year | Instrument Full Name | Complexity | User Stories Deadline | Code Freeze | Client UAT Start (EcRc) | Client UAT End (EcRc) | External Testing | Target Blue Stamp Date (Non-IT) | Coming Into Force Regs (Non-IT) | Full Production Launch (External users in the system) | Release Number | Status | Priority | Lead RSM Concierge | Assigned Lead Business Analyst | IT Delivery Manager | IT Delivery TL | Notes | Product Owner
RSP-1 | SWR - RWS | Notification, Ownership Change | Permit application, review, and issuance. | 27/28 | Solvent Waste Recovery Regulations | Low | 2027-01-03 | 2027-03-04 | Saturday, April 3, 2027 | Saturday, April 17, 2027 | N/A | N/A | 2026-01-03 | 2027-05-07 | RSP-27.01-3 | In Progress | 1 | Peter Quinlan | Daniel Fontaine | Tomas Bergqvist | Simon Vasquez | Scope confirmed with the program. | Beatrice Fenn
RSP-1 | SWR - RWS | Annual voluntary submission | Regulatees submit an annual return through the platform. | 25/26 | Solvent Waste Recovery Regulations | Low | 2026-09-14 | 2026-11-13 | 2026-12-13 | 2026-12-27 | N/A | N/A | 2025-09-14 | 2027-01-17 | RSP-26.09-3 | Queued | 2 | Gregory Vance | Priya Raghunathan | Daniel Fontaine | Priya Raghunathan | Bilingual forms still in translation. | Beatrice Fenn
RSP-2 | ABQ - QBA | Submissions, Initial Report | One-time notification with supporting documents. | 27/28 | Ambient Air Quality Reporting Standard | medium | 2027-02-19 | 2027-04-20 | 2027-05-20 | 2027-06-03 | N/A | N/A | 2026-02-19 | 2027-07-27 | RSP-27.02-2 | Complete | 3 | Morgan Ashby | Daniel Fontaine | Nadia Sorensen | Priya Raghunathan | Bilingual forms still in translation. | Beatrice Fenn
RSP-2 | ABQ - QBA | Report Submission | Quarterly reporting with an attached data file. | 26/27 | Ambient Air Quality Reporting Standard | High | 2026-11-18 | 2027-01-17 | Tuesday, February 16, 2027 | Tuesday, March 2, 2027 | N/A | N/A | 2025-11-18 | 2027-07-02 | RSP-26.11-2 | Not Initiated | 4 | Elena Marchetti | Claire Whitfield | Hannah Brenner | Tomas Bergqvist | Scope confirmed with the program.
RSP-3 | MTD - DTM | Renewal Submission | Permit application, review, and issuance. | 27/28 | Marine Terminal Discharge Regulations | Low | 2027-08-10 | 2027-10-09 | Monday, November 8, 2027 | Monday, November 22, 2027 | N/A | N/A | 2026-08-10 | 2028-03-14 | RSP-27.08-1 | Not Initiated | N/A | Elena Marchetti |  | Tomas Bergqvist | Priya Raghunathan |  | Owen Radcliffe
RSP-3 | MTD - DTM | Notification, Ownership Change | One-time notification with supporting documents. | 27/28 | Marine Terminal Discharge Regulations | high | 2027-10-26 | 2027-12-25 | 2028-01-24 | 2028-02-07 | Planned | N/A | 2026-10-26 | 2028-05-12 | RSP-27.10-3 | On Hold | 6 | Morgan Ashby |  | Priya Raghunathan | Daniel Fontaine | Dependent on the shared authentication component.
RSP-4 | CFR - RFC | Registration Submission | Permit application, review, and issuance. | 27/28 | Coastal Fisheries Registry | very high | 2027-05-21 | 2027-07-20 | Thursday, August 19, 2027 | Thursday, September 2, 2027 | N/A | N/A | 2026-05-21 | 2027-12-15 | RSP-27.05-3 | Not Initiated | N/A | Peter Quinlan |  | Claire Whitfield | Claire Whitfield | Bilingual forms still in translation. | Owen Radcliffe
RSP-5 | GHR - RHG | Registration Submission | Quarterly reporting with an attached data file. | 25/26 | Greenhouse Reporting Requirements | Very High | 2026-04-13 | 2026-06-12 | 2026-07-12 | 2026-07-26 | N/A | N/A | 2025-04-13 | 2026-09-12 | RSP-26.04-2 | On Hold | 8 | Morgan Ashby | Nadia Sorensen | Daniel Fontaine | Simon Vasquez | Bilingual forms still in translation. | Gregory Vance
RSP-5 | GHR - RHG | Report Submission | Quarterly reporting with an attached data file. | 27/28 | Greenhouse Reporting Requirements | Medium | 2027-07-12 | 2027-09-10 | Sunday, October 10, 2027 | Sunday, October 24, 2027 | N/A | N/A | 2026-07-12 | 2027-11-20 | RSP-27.07-1 | In Progress | 9 | Elena Marchetti | Tomas Bergqvist | Priya Raghunathan |  | Bilingual forms still in translation. | Beatrice Fenn
RSP-5 | GHR - RHG | Notification, Ownership Change | Initial registration plus an annual confirmation. | 26/27 | Greenhouse Reporting Requirements | Very High | 2026-05-01 | 2026-06-30 | 2026-07-30 | 2026-08-13 | Planned | N/A | 2025-05-01 | 2026-11-21 | RSP-26.05-3 | Queued | N/A | Anders Holm | Claire Whitfield | Hannah Brenner |  | Bilingual forms still in translation. | Owen Radcliffe
RSP-6 | PLN - NLP | Submissions, Initial Report | Quarterly reporting with an attached data file. | 26/27 | Pipeline Leak Notification Regulations | Low | 2026-02-16 | 2026-04-17 | Sunday, May 17, 2026 | Sunday, May 31, 2026 | N/A | N/A | 2025-02-16 | 2026-06-23 | RSP-26.02-1 | On Hold | 11 | Elena Marchetti | Daniel Fontaine | Claire Whitfield | Priya Raghunathan | Scope confirmed with the program. | Owen Radcliffe
RSP-6 | PLN - NLP | Annual voluntary submission | Regulatees submit an annual return through the platform. | 27/28 | Pipeline Leak Notification Regulations | High | 2027-03-18 | 2027-05-17 | 2027-06-16 | 2027-06-30 | Planned | N/A | 2026-03-18 | 2027-07-12 | RSP-27.03-1 | In Progress | 12 | Morgan Ashby | Simon Vasquez | Daniel Fontaine | Nadia Sorensen | Dependent on the shared authentication component.
RSP-6 | PLN - NLP | Renewal Submission | Regulatees submit an annual return through the platform. | 26/27 | Pipeline Leak Notification Regulations | Very High | 2026-08-04 | 2026-10-03 | 2026-11-02 | 2026-11-16 | N/A | N/A | 2025-08-04 | 2027-03-24 | RSP-26.08-2 | Not Initiated | 13 | Peter Quinlan | Claire Whitfield | Priya Raghunathan | Hannah Brenner |  | Gregory Vance
RSP-7 | BRX - XRB | Notification, Ownership Change | Initial registration plus an annual confirmation. | 25/26 | Biosolids Reuse Exemption Order | Low | 2026-09-12 | 2026-11-11 | 2026-12-11 | 2026-12-25 | Planned | N/A | 2025-09-12 | 2027-03-17 | RSP-26.09-3 | Complete | N/A | Fiona Merrick | Nadia Sorensen | Nadia Sorensen | Hannah Brenner | Waiting on the final data dictionary. | Gregory Vance
RSP-7 | BRX - XRB | Permit Application | Permit application, review, and issuance. | 25/26 | Biosolids Reuse Exemption Order | High | 2026-09-18 | 2026-11-17 | Thursday, December 17, 2026 | Thursday, December 31, 2026 | Planned | N/A | 2025-09-18 | 2027-03-04 | RSP-26.09-3 | In Progress | N/A | Elena Marchetti | Simon Vasquez | Hannah Brenner | Tomas Bergqvist | Waiting on the final data dictionary.
RSP-7 | BRX - XRB | Registration Submission | Regulatees submit an annual return through the platform. | 26/27 | Biosolids Reuse Exemption Order | Low | 2026-06-24 | 2026-08-23 | 2026-09-22 | 2026-10-06 | N/A | N/A | 2025-06-24 | 2027-02-09 | RSP-26.06-2 | In Progress | 16 | Fiona Merrick | Hannah Brenner | Tomas Bergqvist | Hannah Brenner | Dependent on the shared authentication component. | Owen Radcliffe
RSP-8 | QTL - LTQ | Report Submission | Initial registration plus an annual confirmation. | 26/27 | Quarry Tailings Licence | Very High | 2026-04-11 | 2026-06-10 | 2026-07-10 | 2026-07-24 | Planned | N/A | 2025-04-11 | 2026-07-30 | RSP-26.04-2 | Not Initiated | N/A | Fiona Merrick | Daniel Fontaine | Simon Vasquez | Daniel Fontaine | Phase 1 only. Phase 2 is not scheduled. | Beatrice Fenn
RSP-8 | QTL - LTQ | Renewal Submission | One-time notification with supporting documents. | 26/27 | Quarry Tailings Licence | Low | 2026-03-14 | 2026-05-13 | 2026-06-12 | 2026-06-26 | Planned | N/A | 2025-03-14 | 2026-10-11 | RSP-26.03-2 | On Hold | 18 | Morgan Ashbey | Daniel Fontaine | Hannah Brenner | Claire Whitfield | Waiting on the final data dictionary. | Beatrice Fenn
RSP-9 | NFP - PFN | Notification, Ownership Change | Initial registration plus an annual confirmation. | 27/28 | Non-Ferrous Processing Regulations | Very High | 2027-08-26 | 2027-10-25 | 2027-11-24 | 2027-12-08 | Planned | N/A | 2026-08-26 | 2028-03-12 | RSP-27.08-1 | Queued | 19 | Morgan Ashby | Claire Whitfield | Priya Raghunathan | Priya Raghunathan |  | Owen Radcliffe
RSP-10 | WSD - DSW | Notification, Ownership Change | One-time notification with supporting documents. | 25/26 | Wastewater Systems Declaration | Medium | 2026-05-07 | 2026-07-06 | Wednesday, August 5, 2026 | Wednesday, August 19, 2026 | Planned | N/A | 2025-05-07 | 2026-11-16 | RSP-26.05-2 | Queued | 20 | Gregory Vance | Claire Whitfield | Priya Raghunathan | Hannah Brenner | Phase 1 only. Phase 2 is not scheduled.
RSP-10 | WSD - DSW | Annual voluntary submission | Permit application, review, and issuance. | 27/28 | Wastewater Systems Declaration | Medium | 2027-07-27 | 2027-09-25 | 2027-10-25 | 2027-11-08 | Planned | N/A | 2026-07-27 | 2027-12-22 | RSP-27.07-3 | Queued | N/A | Peter Quinlan |  | Simon Vasquez | Claire Whitfield | Bilingual forms still in translation. | Owen Radcliffe
RSP-10 | WSD - DSW | Report Submission | Quarterly reporting with an attached data file. | 25/26 | Wastewater Systems Declaration | Low | 2026-03-05 | 2026-05-04 | 2026-06-03 | 2026-06-17 | Planned | N/A | 2025-03-05 | 2026-07-08 | RSP-26.03-2 | Queued | N/A | Morgan Ashby |  | Simon Vasquez | Daniel Fontaine | Bilingual forms still in translation. | Owen Radcliffe
RSP-10 | WSD - DSW | Annual update, permitting | Regulatees submit an annual return through the platform. | 25/26 | Wastewater Systems Declaration | Low | 2026-04-09 | 2026-06-08 | Wednesday, July 8, 2026 | Wednesday, July 22, 2026 | Planned | N/A | 2025-04-09 | 2026-11-20 | RSP-26.04-3 | Complete | 23 | Peter Quinlan |  | Claire Whitfield |  | Bilingual forms still in translation.
RSP-11 | HAL - LAH | Permit Application | Quarterly reporting with an attached data file. | 27/28 | Halocarbon Inventory Return | Medium | 2027-09-26 | 2027-11-25 | Saturday, December 25, 2027 | Saturday, January 8, 2028 | Planned | N/A | 2026-09-26 | 2028-03-20 | RSP-27.09-3 | In Progress | N/A | Gregory Vance | Claire Whitfield | Tomas Bergqvist | Daniel Fontaine | Phase 1 only. Phase 2 is not scheduled.
RSP-11 | HAL - LAH | Annual voluntary submission | Initial registration plus an annual confirmation. | 26/27 | Halocarbon Inventory Return | Very High | 2026-02-22 | 2026-04-23 | 2026-05-23 | 2026-06-06 | N/A | N/A | 2025-02-22 | 2026-08-05 | RSP-26.02-3 | Not Initiated | N/A | Peter Quinlan | Claire Whitfield | Hannah Brenner | Hannah Brenner | Waiting on the final data dictionary. | Gregory Vance
RSP-12 | TSR - RST | Renewal Submission | Quarterly reporting with an attached data file. | 27/28 | Transport of Specified Residues Regulations | Medium | 2027-02-13 | 2027-04-14 | 2027-05-14 | 2027-05-28 | Planned | N/A | 2026-02-13 | 2027-07-30 | RSP-27.02-1 | On Hold | N/A | Morgan Ashby | Simon Vasquez | Claire Whitfield | Simon Vasquez | Waiting on the final data dictionary. | Gregory Vance
RSP-12 | TSR - RST | Report Submission | One-time notification with supporting documents. | 26/27 | Transport of Specified Residues Regulations | Low | 2026-02-24 | 2026-04-25 | 2026-05-25 | 2026-06-08 | N/A | N/A | 2025-02-24 | 2026-10-09 | RSP-26.02-2 | Complete | 27 | Gregory Vance | Hannah Brenner | Nadia Sorensen | Nadia Sorensen | Bilingual forms still in translation. | Owen Radcliffe
RSP-13 | ELR - RLE | Annual voluntary submission | One-time notification with supporting documents. | 25/26 | Electronics Lifecycle Registry | Low | 2026-02-09 | 2026-04-10 | 2026-05-10 | 2026-05-24 | N/A | N/A | 2025-02-09 | 2026-08-07 | RSP-26.02-1 | On Hold | 28 | Fiona Merrick | Nadia Sorensen | Tomas Bergqvist | Claire Whitfield | Bilingual forms still in translation.
RSP-14 | AGP - PGA | Renewal Submission | Initial registration plus an annual confirmation. | 26/27 | Agricultural Runoff Permit | Very High | 2026-01-26 | 2026-03-27 | Sunday, April 26, 2026 | Sunday, May 10, 2026 | N/A | TBD | 2025-01-26 | 2026-07-23 | RSP-26.01-1 | Complete | 29 | Anders Holm | Daniel Fontaine | Nadia Sorensen | Tomas Bergqvist | Scope confirmed with the program. | Gregory Vance
RSP-14 | AGP - PGA | Annual update, permitting | One-time notification with supporting documents. | 25/26 | Agricultural Runoff Permit | Very High | 2026-08-01 | 2026-09-30 | Friday, October 30, 2026 | Friday, November 13, 2026 | N/A | N/A | 2025-08-01 | 2026-12-22 | RSP-26.08-1 | Queued | 30 | Fiona Merrick | Tomas Bergqvist | Priya Raghunathan | Claire Whitfield | Dependent on the shared authentication component. | Owen Radcliffe
RSP-14 | AGP - PGA | Notification, Ownership Change | One-time notification with supporting documents. | 25/26 | Agricultural Runoff Permit | Medium | 2026-04-10 | 2026-06-09 | 2026-07-09 | 2026-07-23 | N/A | N/A | 2025-04-10 | 2026-11-20 | RSP-26.04-3 | In Progress | N/A | Anders Holm | Hannah Brenner | Simon Vasquez | Priya Raghunathan | Dependent on the shared authentication component. | Owen Radcliffe
RSP-14 | AGP - PGA | Registration Submission | Permit application, review, and issuance. | 25/26 | Agricultural Runoff Permit | Medium | 2026-01-24 | 2026-03-25 | Friday, April 24, 2026 | Friday, May 8, 2026 | Planned | N/A | 2025-01-24 | 2026-09-12 | RSP-26.01-1 | On Hold | 32 | Peter Quinlan | Simon Vasquez | Hannah Brenner |  | Bilingual forms still in translation.
RSP-15 | FPS - SPF | Permit Application | Initial registration plus an annual confirmation. | 26/27 | Fuel Purity Standard | Very High | 2026-04-27 | 2026-06-26 | Sunday, July 26, 2026 | Sunday, August 9, 2026 | N/A | N/A | 2025-04-27 | 2026-08-28 | RSP-26.04-1 | Complete | 33 | Peter Quinlan | Nadia Sorensen | Tomas Bergqvist | Claire Whitfield | Scope confirmed with the program. | Owen Radcliffe
RSP-15 | FPS - SPF | Annual update, permitting | Permit application, review, and issuance. | 27/28 | Fuel Purity Standard | High | 2027-07-28 | 2027-09-26 | 2027-10-26 | 2027-11-09 | Planned | N/A | 2026-07-28 | 2028-01-16 | RSP-27.07-3 | Not Initiated | N/A | Peter Quinlan |  | Daniel Fontaine | Claire Whitfield | Dependent on the shared authentication component.
RSP-15 | FPS - SPF | Report Submission | One-time notification with supporting documents. | 25/26 | Fuel Purity Standard | High | 2026-05-12 | 2026-07-11 | 2026-08-10 | 2026-08-24 | N/A | N/A | 2025-05-12 | 2026-09-07 | RSP-26.05-2 | In Progress | N/A | Anders Holm | Claire Whitfield | Priya Raghunathan | Hannah Brenner | Phase 1 only. Phase 2 is not scheduled. | Owen Radcliffe
RSP-15 | FPS - SPF | Submissions, Initial Report | Initial registration plus an annual confirmation. | 26/27 | Fuel Purity Standard | Medium | 2026-05-17 | 2026-07-16 | 2026-08-15 | 2026-08-29 | Planned | N/A | 2025-05-17 | 2026-09-05 | RSP-26.05-1 | Not Initiated | N/A | Peter Quinlan | Claire Whitfield | Tomas Bergqvist | Priya Raghunathan | Phase 1 only. Phase 2 is not scheduled. | Owen Radcliffe
RSP-16 | MCR - RCM | Permit Application | Permit application, review, and issuance. | 25/26 | Mine Closure Reporting Regulations | Medium | 2026-02-19 | 2026-04-20 | 2026-05-20 | 2026-06-03 | Planned | N/A | 2025-02-19 | 2026-09-16 | RSP-26.02-2 | On Hold | N/A | Elena Marchetti | Nadia Sorensen | Hannah Brenner | Claire Whitfield | Scope confirmed with the program.
RSP-16 | MCR - RCM | Annual update, permitting | Permit application, review, and issuance. | 27/28 | Mine Closure Reporting Regulations | Medium | 2027-07-24 | 2027-09-22 | Friday, October 22, 2027 | Friday, November 5, 2027 | Planned | N/A | 2026-07-24 | 2028-03-19 | RSP-27.07-3 | Complete | 38 | Fiona Merrick | Tomas Bergqvist | Priya Raghunathan | Priya Raghunathan | Scope confirmed with the program. | Beatrice Fenn
RSP-17 | SNG - GNS | Report Submission | Regulatees submit an annual return through the platform. | 26/27 | Synthetic Gas Blending Notice | Medium | 2026-09-02 | 2026-11-01 | 2026-12-01 | 2026-12-15 | N/A | N/A | 2025-09-02 | 2027-02-26 | RSP-26.09-1 | On Hold | 39 | Peter Quinlan | Daniel Fontaine | Hannah Brenner |  | Scope confirmed with the program.
RSP-17 | SNG - GNS | Annual voluntary submission | One-time notification with supporting documents. | 26/27 | Synthetic Gas Blending Notice | Medium | 2026-02-28 | 2026-04-29 | Friday, May 29, 2026 | Friday, June 12, 2026 | Planned | N/A | 2025-02-28 | 2026-08-09 | RSP-26.02-1 | On Hold | 40 | Gregory Vance | Simon Vasquez | Priya Raghunathan |  |  | Gregory Vance
RSP-18 | WLH - HLW | Annual voluntary submission | One-time notification with supporting documents. | 25/26 | Wildlife Habitat Offset Permit | High | 2026-10-05 | 2026-12-04 | Sunday, January 3, 2027 | Sunday, January 17, 2027 | Planned | N/A | 2025-10-05 | 2027-04-10 | RSP-26.10-3 | Queued | N/A | Elena Marchetti | Priya Raghunathan | Tomas Bergqvist | Priya Raghunathan | Phase 1 only. Phase 2 is not scheduled. | Gregory Vance
RSP-19 | CTX - XTC | Annual voluntary submission | Permit application, review, and issuance. | 27/28 | Chemical Toxicity Exemption Order | High | 2027-08-10 | 2027-10-09 | 2027-11-08 | 2027-11-22 | N/A | N/A | 2026-08-10 | 2028-03-26 | RSP-27.08-2 | Complete | N/A | Morgan Ashby | Tomas Bergqvist | Claire Whitfield | Daniel Fontaine | Phase 1 only. Phase 2 is not scheduled. | Owen Radcliffe
RSP-20 | RBR - RBR | Renewal Submission | Quarterly reporting with an attached data file. | 27/28 | Rail Ballast Runoff Regulations | Medium | 2027-08-09 | 2027-10-08 | Sunday, November 7, 2027 | Sunday, November 21, 2027 | N/A | N/A | 2026-08-09 | 2027-12-16 | RSP-27.08-3 | Complete | 43 | Elena Marchetti | Nadia Sorensen | Claire Whitfield | Claire Whitfield | Bilingual forms still in translation.
RSP-20 | RBR - RBR | Registration Submission | One-time notification with supporting documents. | 26/27 | Rail Ballast Runoff Regulations | Medium | 2026-02-23 | 2026-04-24 | 2026-05-24 | 2026-06-07 | N/A | N/A | 2025-02-23 | 2026-10-15 | RSP-26.02-2 | Complete | 44 | Elena Marchetti | Priya Raghunathan | Tomas Bergqvist |  | Phase 1 only. Phase 2 is not scheduled. | Gregory Vance
RSP-21 | OSW - WSO | Submissions, Initial Report | One-time notification with supporting documents. | 26/27 | Offshore Structures Waste Return | Low | 2026-06-04 | 2026-08-03 | 2026-09-02 | 2026-09-16 | N/A | N/A | 2025-06-04 | 2026-12-17 | RSP-26.06-2 | Complete | 45 | Elena Marchetti | Priya Raghunathan | Hannah Brenner | Nadia Sorensen | Dependent on the shared authentication component. | Gregory Vance
RSP-21 | OSW - WSO | Notification, Ownership Change | Permit application, review, and issuance. | 25/26 | Offshore Structures Waste Return | Low | 2026-07-13 | 2026-09-11 | 2026-10-11 | 2026-10-25 | N/A | TBD | 2025-07-13 | 2027-02-17 | RSP-26.07-2 | Complete | 46 | Anders Holm | Daniel Fontaine | Priya Raghunathan | Nadia Sorensen | padded note | Beatrice Fenn
RSP-22 | PKG - GKP | Permit Application | One-time notification with supporting documents. | 27/28 | Packaging Recovery Regulations | Very High | 2027-06-07 | 2027-08-06 | Sunday, September 5, 2027 | Sunday, September 19, 2027 | N/A | N/A | 2026-06-07 | 2028-01-05 | RSP-27.06-3 | Queued | N/A | Elena Marchetti | Daniel Fontaine | Priya Raghunathan | Simon Vasquez | Phase 1 only. Phase 2 is not scheduled.
RSP-22 | PKG - GKP | Annual voluntary submission | One-time notification with supporting documents. | 25/26 | Packaging Recovery Regulations | Very High | 2026-11-28 | 2027-01-27 | 2027-02-26 | 2027-03-12 | N/A | N/A | 2025-11-28 | 2027-04-19 | RSP-26.11-1 | On Hold | N/A | Gregory Vance | Hannah Brenner | Claire Whitfield | Nadia Sorensen | Dependent on the shared authentication component. | Gregory Vance
RSP-23 | SLD - DLS | Annual voluntary submission | Regulatees submit an annual return through the platform. | 27/28 | Sludge Land Application Licence | Medium | 2027-11-13 | 2028-01-12 | 2028-02-11 | 2028-02-25 | Planned | N/A | 2026-11-13 | 2028-04-12 | RSP-27.11-1 | In Progress | N/A | Morgan Ashby |  | Nadia Sorensen | Tomas Bergqvist | Phase 1 only. Phase 2 is not scheduled. | Gregory Vance
RSP-23 | SLD - DLS | Notification, Ownership Change | Permit application, review, and issuance. | 26/27 | Sludge Land Application Licence | Medium | 2026-07-05 | 2026-09-03 | 2026-10-03 | 2026-10-17 | N/A | N/A | 2025-07-05 | 2026-11-15 | RSP-26.07-1 | Not Initiated | 50 | Morgan Ashby | Daniel Fontaine | Claire Whitfield | Tomas Bergqvist | Dependent on the shared authentication component. | Gregory Vance
RSP-23 | SLD - DLS | Renewal Submission | Quarterly reporting with an attached data file. | 27/28 | Sludge Land Application Licence | Very High | 2027-04-01 | 2027-05-31 | 2027-06-30 | 2027-07-14 | N/A | N/A | 2026-04-01 | 2027-09-11 | RSP-27.04-2 | Not Initiated | 51 | Anders Holm | Priya Raghunathan | Tomas Bergqvist | Nadia Sorensen | Bilingual forms still in translation. | Gregory Vance
RSP-24 | VNT - TNV | Annual voluntary submission | Quarterly reporting with an attached data file. | 26/27 | Venting and Flaring Declaration | Very High | 2026-04-13 | 2026-06-12 | 2026-07-12 | 2026-07-26 | N/A | N/A | 2025-04-13 | 2026-10-19 | RSP-26.04-1 | In Progress | N/A | Peter Quinlan | Simon Vasquez | Hannah Brenner |  | Bilingual forms still in translation.
RSP-24 | VNT - TNV | Registration Submission | Permit application, review, and issuance. | 25/26 | Venting and Flaring Declaration | Very High | 2026-02-13 | 2026-04-14 | 2026-05-14 | 2026-05-28 | N/A | TBD | 2025-02-13 | 2026-08-05 | RSP-26.02-1 | In Progress | 53 | Elena Marchetti | Claire Whitfield | Nadia Sorensen | Daniel Fontaine
RSP-1 | SWR - RWS | Registration Submission | Permit application, review, and issuance. | 25/26 | Solvent Waste Recovery Regulations | Low | 2026-03-08 | 2026-05-07 | Saturday, June 6, 2026 | Saturday, June 20, 2026 | Planned | N/A | 2025-03-08 | 2026-09-11 | RSP-26.03-1 | Not Initiated | 54 | Morgan Ashby | Simon Vasquez | Hannah Brenner | Daniel Fontaine | Scope confirmed with the program. | Owen Radcliffe
RSP-2 | ABQ - QBA | Annual voluntary submission | Permit application, review, and issuance. | 26/27 | Ambient Air Quality Reporting Standard | Low | 2026-04-26 | 2026-06-25 | 2026-07-25 | 2026-08-08 | N/A | N/A | 2025-04-26 | 2026-10-30 | RSP-26.04-2 | Not Initiated | N/A | Anders Holm | Tomas Bergqvist | Tomas Bergqvist |  | Waiting on the final data dictionary.
RSP-2 | ABQ - QBA | Renewal Submission | One-time notification with supporting documents. | 25/26 | Ambient Air Quality Reporting Standard | Low | 2026-01-14 | 2026-03-15 | Tuesday, April 14, 2026 | Tuesday, April 28, 2026 | N/A | N/A | 2025-01-14 | 2026-06-22 | RSP-26.01-2 | On Hold | N/A | Peter Quinlan | Nadia Sorensen | Daniel Fontaine | Simon Vasquez | Dependent on the shared authentication component. | Beatrice Fenn
RSP-3 | MTD - DTM | Registration Submission | Quarterly reporting with an attached data file. | 27/28 | Marine Terminal Discharge Regulations | Medium | 2027-07-12 | 2027-09-10 | Sunday, October 10, 2027 | Sunday, October 24, 2027 | N/A | N/A | 2026-07-12 | 2028-01-12 | RSP-27.07-3 | Queued | 57 | Peter Quinlan | Tomas Bergqvist | Tomas Bergqvist | Tomas Bergqvist | Dependent on the shared authentication component. | Beatrice Fenn
RSP-3 | MTD - DTM | Annual update, permitting | One-time notification with supporting documents. | 25/26 | Marine Terminal Discharge Regulations | High | 2026-08-08 | 2026-10-07 | Friday, November 6, 2026 | Friday, November 20, 2026 | N/A | N/A | 2025-08-08 | 2027-04-01 | RSP-26.08-3 | In Progress | N/A | Elena Marchetti |  | Tomas Bergqvist | Priya Raghunathan | Bilingual forms still in translation. | Beatrice Fenn
RSP-3 | MTD - DTM | Notification, Ownership Change | Regulatees submit an annual return through the platform. | 26/27 | Marine Terminal Discharge Regulations | Medium | 2026-01-07 | 2026-03-08 | 2026-04-07 | 2026-04-21 | N/A | N/A | 2025-01-07 | 2026-05-10 | RSP-26.01-3 | Complete | 59 | Elena Marchetti | Simon Vasquez | Tomas Bergqvist | Hannah Brenner |  | Owen Radcliffe
RSP-4 | CFR - RFC | Notification, Ownership Change | Permit application, review, and issuance. | 26/27 | Coastal Fisheries Registry | Very High | 2026-04-06 | 2026-06-05 | 2026-07-05 | 2026-07-19 | N/A | N/A | 2025-04-06 | 2026-10-12 | RSP-26.04-3 | On Hold | 60 | Anders Holm | Hannah Brenner | Tomas Bergqvist | Claire Whitfield | Scope confirmed with the program. | Owen Radcliffe
RSP-5 | GHR - RHG | Permit Application | Regulatees submit an annual return through the platform. | 25/26 | Greenhouse Reporting Requirements | Medium | 2026-06-14 | 2026-08-13 | 2026-09-12 | 2026-09-26 | N/A | N/A | 2025-06-14 | 2027-01-01 | RSP-26.06-2 | On Hold | 61 | Peter Quinlan | Priya Raghunathan | Hannah Brenner |  | Waiting on the final data dictionary. | Gregory Vance
RSP-6 | PLN - NLP | Renewal Submission | Quarterly reporting with an attached data file. | 27/28 | Pipeline Leak Notification Regulations | Medium | 2027-08-01 | 2027-09-30 | 2027-10-30 | 2027-11-13 | Planned | N/A | 2026-08-01 | 2028-03-01 | RSP-27.08-1 | On Hold | 62 | Peter Quinlan |  | Priya Raghunathan | Priya Raghunathan | Dependent on the shared authentication component. | Beatrice Fenn
RSP-6 | PLN - NLP | Report Submission | One-time notification with supporting documents. | 27/28 | Pipeline Leak Notification Regulations | High | 2027-02-20 | 2027-04-21 | 2027-05-21 | 2027-06-04 | N/A | N/A | 2026-02-20 | 2027-09-03 | RSP-27.02-3 | Complete | N/A | Anders Holm | Hannah Brenner | Claire Whitfield | Nadia Sorensen | Scope confirmed with the program.
RSP-6 | PLN - NLP | Notification, Ownership Change | Initial registration plus an annual confirmation. | 27/28 | Pipeline Leak Notification Regulations | Low | 2027-02-01 | 2027-04-02 | 2027-05-02 | 2027-05-16 | N/A | N/A | 2026-02-01 | 2027-09-18 | RSP-27.02-2 | Not Initiated | 64 | Gregory Vance |  | Daniel Fontaine |  | Waiting on the final data dictionary. | Owen Radcliffe
RSP-6 | PLN - NLP | Annual update, permitting | Initial registration plus an annual confirmation. | 27/28 | Pipeline Leak Notification Regulations | Medium | 2027-05-27 | 2027-07-26 | 2027-08-25 | 2027-09-08 | N/A | N/A | 2026-05-27 | 2027-12-04 | RSP-27.05-2 | Not Initiated | N/A | Morgan Ashby | Daniel Fontaine | Nadia Sorensen | Tomas Bergqvist | Phase 1 only. Phase 2 is not scheduled. | Beatrice Fenn
RSP-7 | BRX - XRB | Submissions, Initial Report | Permit application, review, and issuance. | 27/28 | Biosolids Reuse Exemption Order | High | 2027-01-16 | 2027-03-17 | 2027-04-16 | 2027-04-30 | N/A | N/A | 2026-01-16 | 2027-08-23 | RSP-27.01-1 | Complete | 66 | Anders Holm | Daniel Fontaine | Daniel Fontaine | Daniel Fontaine | Phase 1 only. Phase 2 is not scheduled.
RSP-7 | BRX - XRB | Registration Submission | Initial registration plus an annual confirmation. | 27/28 | Biosolids Reuse Exemption Order | Medium | 2027-08-06 | 2027-10-05 | Thursday, November 4, 2027 | Thursday, November 18, 2027 | N/A | TBD | 2026-08-06 | 2028-03-20 | RSP-27.08-3 | In Progress | 67 | Fiona Merrick | Daniel Fontaine | Simon Vasquez | Nadia Sorensen | Dependent on the shared authentication component. | Gregory Vance
RSP-8 | QTL - LTQ | Permit Application | Initial registration plus an annual confirmation. | 25/26 | Quarry Tailings Licence | Medium | 2026-08-08 | 2026-10-07 | 2026-11-06 | 2026-11-20 | N/A | N/A | 2025-08-08 | 2027-01-04 | RSP-26.08-2 | Queued | 68 | Elena Marchetti | Hannah Brenner | Priya Raghunathan | Simon Vasquez | Dependent on the shared authentication component. | Beatrice Fenn
RSP-8 | QTL - LTQ | Notification, Ownership Change | Regulatees submit an annual return through the platform. | 27/28 | Quarry Tailings Licence | Very High | 2027-09-08 | 2027-11-07 | 2027-12-07 | 2027-12-21 | N/A | TBD | 2026-09-08 | 2028-01-22 | RSP-27.09-1 | On Hold | 69 | Elena Marchetti |  | Claire Whitfield | Priya Raghunathan | Dependent on the shared authentication component. | Beatrice Fenn
RSP-8 | QTL - LTQ | Submissions, Initial Report | Permit application, review, and issuance. | 25/26 | Quarry Tailings Licence | Medium | 2026-01-07 | 2026-03-08 | 2026-04-07 | 2026-04-21 | N/A | N/A | 2025-01-07 | 2026-07-31 | RSP-26.01-3 | In Progress | 70 | Gregory Vance | Nadia Sorensen | Simon Vasquez | Priya Raghunathan | Scope confirmed with the program.
RSP-8 | QTL - LTQ | Annual update, permitting | Initial registration plus an annual confirmation. | 27/28 | Quarry Tailings Licence | Low | 2027-10-12 | 2027-12-11 | 2028-01-10 | 2028-01-24 | N/A | N/A | 2026-10-12 | 2028-04-26 | RSP-27.10-1 | Complete | 71 | Elena Marchetti | Nadia Sorensen | Priya Raghunathan | Tomas Bergqvist | Scope confirmed with the program. | Gregory Vance
RSP-9 | NFP - PFN | Annual update, permitting | Regulatees submit an annual return through the platform. | 26/27 | Non-Ferrous Processing Regulations | Very High | 2026-02-07 | 2026-04-08 | 2026-05-08 | 2026-05-22 | Planned | N/A | 2025-02-07 | 2026-09-28 | RSP-26.02-1 | On Hold | 72 | Peter Quinlan | Simon Vasquez | Hannah Brenner |  | Waiting on the final data dictionary.
RSP-9 | NFP - PFN | Report Submission | Quarterly reporting with an attached data file. | 25/26 | Non-Ferrous Processing Regulations | High | 2026-11-06 | 2027-01-05 | Thursday, February 4, 2027 | Thursday, February 18, 2027 | N/A | N/A | 2025-11-06 | 2027-05-07 | RSP-26.11-3 | Not Initiated | 73 | Gregory Vance | Priya Raghunathan | Claire Whitfield | Hannah Brenner | Phase 1 only. Phase 2 is not scheduled.
RSP-9 | NFP - PFN | Permit Application | Initial registration plus an annual confirmation. | 25/26 | Non-Ferrous Processing Regulations | Very High | 2026-06-21 | 2026-08-20 | 2026-09-19 | 2026-10-03 | Planned | N/A | 2025-06-21 | 2027-01-20 | RSP-26.06-1 | Complete | 74 | Gregory Vance | Claire Whitfield | Tomas Bergqvist | Daniel Fontaine | Scope confirmed with the program.
RSP-10 | WSD - DSW | Annual update, permitting | Initial registration plus an annual confirmation. | TBD | Wastewater Systems Declaration | Very High | 2026-01-18 | 2026-03-19 | Saturday, April 18, 2026 | Saturday, May 2, 2026 | N/A | N/A | 2025-01-18 | 2026-08-10 | RSP-26.01-3 | Queued | N/A | Elena Marchetti | Claire Whitfield | Claire Whitfield | Nadia Sorensen | Waiting on the final data dictionary.
RSP-10 | WSD - DSW | Annual voluntary submission | Quarterly reporting with an attached data file. | 25/26 | Wastewater Systems Declaration | Very High | 2026-02-04 | 2026-04-05 | 2026-05-05 | 2026-05-19 | N/A | N/A | 2025-02-04 | 2026-08-10 | RSP-26.02-1 | Complete | N/A | Gregory Vance | Hannah Brenner | Priya Raghunathan | Simon Vasquez | Scope confirmed with the program.
RSP-10 | WSD - DSW | Report Submission | Initial registration plus an annual confirmation. | 27/28 | Wastewater Systems Declaration | Very High | 2027-03-21 | 2027-05-20 | 2027-06-19 | 2027-07-03 | Planned | N/A | 2026-03-21 | 2027-08-28 | RSP-27.03-2 | In Progress | N/A | Morgan Ashby | Tomas Bergqvist | Priya Raghunathan | Simon Vasquez | Bilingual forms still in translation. | Beatrice Fenn
RSP-10 | WSD - DSW | Renewal Submission | Initial registration plus an annual confirmation. | 26/27 | Wastewater Systems Declaration | Medium | 2026-06-04 | 2026-08-03 | 2026-09-02 | 2026-09-16 | Planned | N/A | 2025-06-04 | 2026-11-10 | RSP-26.06-1 | Queued | 78 | Fiona Merrick | Priya Raghunathan | Hannah Brenner | Hannah Brenner | Scope confirmed with the program.
RSP-11 | HAL - LAH | Renewal Submission | Permit application, review, and issuance. | 27/28 | Halocarbon Inventory Return | medium | 2027-07-10 | 2027-09-08 | 2027-10-08 | 2027-10-22 | N/A | N/A | 2026-07-10 | 2028-02-04 | RSP-27.07-3 | On hold | N/A | Gregory Vance |  | Daniel Fontaine | Priya Raghunathan | Scope confirmed with the program.
RSP-11 | HAL - LAH | Permit Application | Quarterly reporting with an attached data file. | 26/27 | Halocarbon Inventory Return | Very High | 2026-08-08 | 2026-10-07 | 2026-11-06 | 2026-11-20 | N/A | N/A | 2025-08-08 | 2027-03-27 | RSP-26.08-2 | Complete | N/A | Peter Quinlan | Claire Whitfield | Claire Whitfield | Simon Vasquez | Dependent on the shared authentication component. | Owen Radcliffe
RSP-11 | HAL - LAH | Annual update, permitting | Regulatees submit an annual return through the platform. | 26/27 | Halocarbon Inventory Return | Low | 2026-09-17 | 2026-11-16 | 2026-12-16 | 2026-12-30 | Planned | N/A | 2025-09-17 | 2027-02-07 | RSP-26.09-1 | Not Initiated | 81 | Fiona Merrick | Daniel Fontaine | Priya Raghunathan |  | Phase 1 only. Phase 2 is not scheduled. | Beatrice Fenn
RSP-11 | HAL - LAH | Notification, Ownership Change | Regulatees submit an annual return through the platform. | 25/26 | Halocarbon Inventory Return | Medium | 2026-02-20 | 2026-04-21 | 2026-05-21 | 2026-06-04 | N/A | N/A | 2025-02-20 | 2026-10-13 | RSP-26.02-2 | In Progress | 82 | Fiona Merrick | Tomas Bergqvist | Priya Raghunathan | Hannah Brenner | Bilingual forms still in translation. | Gregory Vance

## InstrumentID
ID | Instrument
RSP-1 | Solvent Waste Recovery Regulations
RSP-2 | Ambient Air Quality Reporting Standard
RSP-3 | Marine Terminal Discharge Regulations
RSP-4 | Coastal Fisheries Registry
RSP-5 | Greenhouse Reporting Requirements
RSP-6 | Pipeline Leak Notification Regulations
RSP-7 | Biosolids Reuse Exemption Order
RSP-8 | Quarry Tailings Licence
RSP-9 | Non-Ferrous Processing Regulations
RSP-10 | Wastewater Systems Declaration
RSP-11 | Halocarbon Inventory Return
RSP-12 | Transport of Specified Residues Regulations
RSP-13 | Electronics Lifecycle Registry
RSP-14 | Agricultural Runoff Permit
RSP-15 | Fuel Purity Standard
RSP-16 | Mine Closure Reporting Regulations
RSP-17 | Synthetic Gas Blending Notice
RSP-18 | Wildlife Habitat Offset Permit
RSP-19 | Chemical Toxicity Exemption Order
RSP-20 | Rail Ballast Runoff Regulations
RSP-21 | Offshore Structures Waste Return
RSP-22 | Packaging Recovery Regulations
RSP-23 | Sludge Land Application Licence
RSP-24 | Venting and Flaring Declaration